## Abilene
Abilene District
| County | Project ID | Segment | Project | Estimated Let Date | Amount | Description | UTP Action | Status | Bid Target | Comments
Abilene District | Howard | 0069-01-061 | US 87 | Widen Non-Freeway- Big Spring FROM 2 miles North of Glasscock CO TO Glasscock CO | FY 2025-2028 | 16240000 | Widen Road - Add Lanes And Shoulders | Cat. 4 Rural $16,240,000 TOTAL $16,240,000 Cat. 4R increased $5.7M | Construction begins within 4 years | 2026-09-01 | Bid Delayed from 3/17/25
Abeline District | Glasscock | 0069-02-030 | US 87 | Howard County Line to 0.45 Miles South of Howard County Line | FY 2025-2028 | 3584000 | Widen Non-Freeway | Cat. 4 Rural $3,584,000 TOTAL $3,584,000 Cat. 4R increased $1M | Construction Begins within 4-years | 2026-09-01 | Bid Delayed from 3/17/25
[6 empty] | Total District | Change from Previous Year
2025 TOTAL Abilene District Less TBD | [5 empty] | 19824000 | 3584000
2024 TOTAL Abilene District Less TBD | [5 empty] | 16240000 | 3240000
2023 TOTAL Abilene District Less TBD | [5 empty] | 13000000
Comments: North Big Spring Reliever Route completed in 2020

## Amarillo
Amarillo District
| County | Project ID | Segment | Project | Estimated Let Date | Amount | Description | UTP Action | Status | Bid Target | Comments
Amarillo | Hartley | 0425-01-021 | US 87 | US 87 - Widen Non-Freeway ¦ Limits From: EAST OF US385/US87 INTERCHANGE To: MOORE COUNTY LINE | FY 2025-2028 | 110024022 | CONSTRUCT FROM 2-LANE TO 4-LANE DIVIDE, ADD CENTER LEFT TURN LANES, ACP OVERLAY AND UPGRADE STANDARDS - HARTLEY COUNTY | Cat. 4 Rural $110,024,022 TOTAL $110,024,022 Cat. 4R increased $6.0M | Construction Begins within 4-years | 2025-05-01 | Bid delayed from 2/23/2024 to 5/1/2025
Amarillo | Moore | 0425-02-037 | US 87 | US 87 - Widen Non-Freeway ¦ Limits From: HARTLEY COUNTY LINE Limits To: FM 2589 WEST OF DUMAS | FY 2025-20278 | 55364831 | CONSTRUCT FROM 2-LANE TO 4-LANE DIVIDE, ADD CENTER LEFT TURN LANES, ACP OVERLAY AND UPGRADE STANDARDS - MOORE COUNTY | Cat. 4 Rural $55,364,831 TOTAL $55,364,831 Cat. 4R increased $6.0M | Construction Begins within 4-years | 2025-05-01 | Bid delayed from 2/23/2024 to 5/1/2025
Amarillo | Randall | 0067-17-032 | I-27 | IH 27 - Widen Freeway - Amarillo to Canyon ¦ Limits From: NORTH OF US 60/US 87 INTERCHANGE Limits To: SOUTH OF US 60/US 87 INTERCHANGE |  | 46100000 | CONSTRUCT NEW ROAD |  | Under Construction |  | Notice to proceed dated 4/25/2024
Amarillo | Randall | 0168-09-083 | I-27 | IH 27 - Widen Freeway - Amarillo to Canyon ¦ Limits From: SOUTH OF SUNDOWN Limits To: NORTH OF US 60/US 87 INTERCHANGE | 269063384 | 222963384 | WIDEN FREEWAY FROM 4-LANES TO 6-LANES |  | Under Construction |  | Notice to proceed dated 4/25/2024
Amarillo | Randall | 0168-09-186 | I-27 | SL 335 / I-27 Interchange Phase II: Sundown Ln to SL 335 | FY 2025-2028 | 18572730 | Rehabilitate Existing Roadway | Cat. 2 Metro/Urban Corridor $7,392,000 Cat. 12 Strategic Priority $11,180,730 TOTAL $18,572,730 Cat. 12 added $11.2M | Construction begins within 4 years
Amarillo | Randall | 2635-02-034 | SL 335 | SL 335 / I-27 Interchange Phase II: I-27 to Bell St | 2025-2028 | 29113323 | Construct New Road | Cat. 2 Metro/Urban Corridor $12,055,680 Cat. 12 Strategic Priority $17,057,643 TOTAL $29,113,323 | Construction begins within 4 years | 2027-09-01
Amarillo | Randall | 2635-03-023 | SL 335 | SL 335 / I-27 Interchange Phase II:East of Coulter to I-27 | FY 2025-2028 | 27518878 | Construct New Road | Cat. 2 Metro/Urban Corridor $5,925,184 Cat. 12 Strategic Priority $21,593,694 TOTAL $27,518,878 | Construction begins within 4 years | 2027-09-01
Amarillo | Randall | 2635-03-028 | SL 335 | SL 335 / I-27 Interchange Phase II: I-27 to Coulter | FY 2025-2028 | 163127301 | Construct Direct Connectors | Cat. 2 Metro/Urban Corridor $16,647,000 Cat. 4 Urban $16,779,000 Cat. 12 Strategic Priority $129,701,301 TOTAL $163,127,301 | Construction begins within 4 years | 2027-09-01
Amarillo | Randall | 2494-02-011 | SL 335 | West of FM 2590 (South) to FM 2186 | FY 2029-2034 | 27108726 | Upgrade to Freeway- Amarillo | Cat. 2 Metro/Urban Corridor $3,409,898 Cat. 4 Urban $1,539 --Remaining funding TBD-- $23,697,289 TOTAL $27,108,726 | Construction begins in 5 to 10 years | 2033-01-01
Amarillo | Randall | 2635-05-004 | SL 335 | FM 2186 to North of FM 2186 | FY 2029-2034 | 26842469 | Upgrade to Freeway- Amarillo | Cat. 2 Metro/Urban Corridor $3,409,898 --Remaining funding TBD-- $23,432,571 TOTAL $26,842,469 | Construction begins in 5 to 10 years | 2033-01-01
Amarillo | Randall | 2635-05-005 | SL 335 | North of FM 2186 to North of Arden Road | FY 2029-2034 | 53497759 | Upgrade to Freeway- Amarillo | Cat. 2 Metro/Urban Corridor $6,819,796 --Remaining funding TBD-- $46,677,963 TOTAL $53,497,759 | Construction begins in 5 to 10 years | 2033-01-01
Amarillo | Randall | 2635-05-006 | SL 335 | North of Arden Road to North of Hillside Road | FY 2029-2034 | 49696943 | Upgrade to Freeway- Amarillo | Cat. 4 Urban $7,636,456 --Remaining funding TBD-- $42,060,487 TOTAL $49,696,943 | Construction begins in 5 to 10 years | 2033-01-01 | New Authorization
Sub-total US 87 | [5 empty] | 165388853
Sub-total SL 335 | [5 empty] | 241037099
Sub-total I-27 | [5 empty] | 18572730
2025 TOTAL Amarillo District Less TBD | [5 empty] | 424998682 | -258777099
2024 TOTAL Amarillo District Less TBD | [5 empty] | 683775781 | 185616830
2023 TOTAL Amarillo District Less TBD | [5 empty] | 498158951 | 132340343
2022 TOTAL Amarillo District Less TBD | [5 empty] | 365818608 | -24891392
2021 TOTAL Amarillo District | [5 empty] | 390710000 | 20700000
2020 TOTAL Amarillo District | [5 empty] | 370010000

## Lubbock
District | County | Project ID | Segment | Project | Estimated Let Date | Amount | Description | Status | Bid Target | UTP Action | Comments
Lubbock District
Lubbock | Dawson | 0068-05-040 | US 87 | CR 1026 to US 180 - Dawson County | 13080442 | 10020228 | Widen Non-Freeway | Under Construction | 2024-04-01 |  | Notice to Proceed: 5/8/2024
Lubbock | Dawson | 0068-12-012 | US 87 | N 5th Street to N 3rd Street in Lamesa | FY 2024-2027 | 3060214 | Intersection & Operational Improvements | Under Construction | 2026-01-15 |  | Notice to Proceed:5/8/2024
Lubbock | Lubbock | 0068-01-073 | US 87 | SL88 Lubbock Outer Loop ¦ FROM 114TH STREET TO 146TH STREET | FY 2025-2028 | 144273408 | Construct Bridge | Construction Begins within 4-years | 2026-10-01 | Cat. 1 $34,307,341 Cat. 2 Metro/Urban Corridor $11,304,292 Cat. 4 Urban $73,826,536 Cat. 9 $3,502,746 Cat. 11 Energy Sector $21,332,493 TOTAL $144,273,408 Cat. 2 added $11.3M and Cat. 4U increased $14.8M |  | Approved FY 23 Appropriations $2,000,000
Lubbock | Lubbock | 1502-01-031 | FM 1585 | SL 88 - Lubbock Outer Loop ¦ Limits From: CR 2240 (AVE U) Limits To: 0.5 MI EAST OF US 87 | FY 2024-2027 | 180330075 | CONVERT NON-FREEWAY TO FREEWAY | Construction Begins within 4-years | 2026-10-01 | Cat. 1 $31,758,972 Cat. 2 Metro/Urban Corridor $59,420,550 Cat. 4 Urban $35,443,860 Cat. 7.$19,500,000 Cat. 9 $2,211,58 2 Cat. 11 Energy Sector $31,995,111 TOTAL $180,330,075 |  | Approved FY 23 Appropriations $2,000,000
Sub-total SL 88 | [5 empty] | 180330075
Sub-total US 87 | [5 empty] | 144273408
2025 Total Lubbock District Less TBD | [5 empty] | 324603483 | -84762075
2024 Total Lubbock District Less TBD | [5 empty] | 409365558 | -79627128
2024 Total Lubbock District Less TBD | [5 empty] | 488992686 | 269802660
2023 Total Lubbock District Less TBD | [5 empty] | 219190026 | -81596948
2022 Total Lubbock District Less TBD | [5 empty] | 300786974 | 120456899
2021 TOTAL Lubbock District | [5 empty] | 180330075 | -1589925
2020 TOTAL Lubbock District | [5 empty] | 181920000

## San Angelo
San Angelo District
| County | Project ID | Segment | Project | Estimated Let Date | Amount | Description | UTP Action | Status | Bid Target | Comments
San Angelo | Tom Green | 0264-06-044 | US 277 | US 277 - Operational Improvements ¦ Limits From: 0.75 MILES NORTH OF FM 2105 Limits To: US 67 | FY 2025-2028 | 25057190 | GRADING, STRUCTURES, BASE, SURFACING | Cat. 2 Metro/Urban Corridor $21,456,959 Cat. 4 Urban $3,600,231 TOTAL $25,057,190 Cat. 2 increased $10.1M | Construction Begins within 4-years | 2026-05-01 | Not included in I-27 System in Texas SAN ANGELO DISTRICT
| Glasscock | 0069-02-030 | US 87 | Howard County Line to 0.45 Miles South of Howard County Line | [6 empty] | 2025 UTP shows this project in Abilene District - included in I-27 System in Texas SAN ANGELO DISTRICT
Sub-total SH 158 | [5 empty] | 0
Sub-total US 277 | [5 empty] | 25057190
Sub-total US 87 | [5 empty] | 0
2025 Total San Angelo District less TBD | [5 empty] | 25057190 | 6472958
2024 Total San Angelo District less TBD | [5 empty] | 18584232 | 3584000
2023 Total San Angelo District less TBD | [5 empty] | 15000232

## Odessa
Odessa District
District | County | Project ID | Segment | Project | Estimated Let Date | Amount | Description | UTP Action | Status | Bid Target | Comments
Odessa | Midland | 0005-15-093 | I-20 | I-20 - EAST OF SH 349 to EAST OF FM 1208 | FY 2029-2034 | 577934843 | Widen Road - Add Lanes | Cat. 12 Strategic Priority $13,750,000 Cat. 12 Permian $58,250,000 --Remaining funding TBD-- $505,934,843 TOTAL $577,934,843 | Construction begins in 5 to 10 years | 2030-01-01 | Delayed rom 05/26/28
Odessa | Midland | 0005-14-092 | I-20 | I-20 - EAST OF CR 1250 to EAST OF SH 349 | FY 2025-2028 | 222538627 | Widen Road - Add Lanes | Cat. 2 Metro/Urban Corridor $12,340,792 Cat. 12 Strategic Priority $179,148,763 Cat. 12 Permian $31,049,071 TOTAL $222,538,626 | Construction begins in 5 to 10 years | 2027-01-01
Odessa | Midland | 0005-14-094 | I-20 | I-20 - EAST of CR 1300 to EAST of CR1250 |  | 202949834 | Widen Road - Add Lanes |  | Construction underway or begins soon |  | Notice to proceed dated 4/11/2024 | Under Construction
Odessa | Midland | 1718-07-047 | SH 349 | At FM 1788 | FY 2029-2034 | 5000000 | Intersection & Operational Improvements | Cat. 2 Metro/Urban Corridor $5,000,000 TOTAL $5,000,000 | Construction begins in 5-10 Years | 2033-01-01
Sub-total I-20 | [5 empty] | 294538627
Sub-total SH 158 | [5 empty] | 0
Sub-total SH 349 | [5 empty] | 5000000
2025 Total Odessa District Less TBA | [5 empty] | 299538627 | -115913705
2024 Total Odessa District Less TBA | [5 empty] | 415452332 | 247061259
2023 Total Odessa District Less TBA | [5 empty] | 168391073
.

## Laredo
Laredo District
District | County | Project ID | Segment | Project | Estimated Let Date | Amount | Description | UTP Action | Status | Bid Target | Comments
Laredo | Webb | 0018-05-089 | IH 35 | IH 35 - Bridge Replacement - Uniroyal Drive ¦ Limits From: 0.500 MI S OF UNIROYAL INTERCHANGE Limits To: 2.68 MI N OF UNIROYAL INTERCHANGE | FY 2025-2028 | 254133312 | REPLACEMENT OF EXISTING BRIDGE | Cat. 4 Urban $37,000,000 Cat. 12 Strategic Priority $217,133,312 TOTAL $254,133,312 Cat. 4U added $37.0M and Cat. 12 increased $116.2M |  | 2025-02-01 | Delayed from 9/20/2022 to 2/1/2025
Laredo | Webb | 0018-05-094 | IH 35 | IH 35 - Widen Freeway - Laredo North ¦ Limits From: 2.68 MI N OF UNIROYAL INT(MM 16.0) Limits To: 1.2 MI N OF US 83 INT(MM 19.674) | FY 2025-2028 | 270752005 | OVERPASS REPLACEMENT AND WIDENING OF FREEWAY (6 LANES) | Cat. 4 Rural $232,285,932 Cat. 12 Strategic Priority $38,466,073 TOTAL $270,752,005 Cat. 4R increased $65.0M | Construction begins within 4 Years | 2026-09-01
Laredo | Webb | 0018-06-185 | IH 35 | IH 35 - US 59 Interchange ¦ Limits From: 0.50 MI EAST OF IH35 Limits To: 0.50 MI NORTH OF US59 | FY 2025-2028 | 113505334 | FOR THE CONSTRUCTION OF DIRECT CONNECTOR INTERCHANGE(DC#3) | Cat. 11 Border $20,000,000 Cat. 12 Strategic Priority $93,505,334 TOTAL $113,505,334 Cat. 12 increased $52.0M | Construction begins within 4 Years | 2025-11-01 | Delayed from 1/25/2023 to 11/1/2025
Laredo | Webb | 0037-10-041 | US 83 | Los Botines Ln to US 83 / IH 35 Underpass | FY 2025-2028 | 270752005 | Widen Non-Freeway | Cat. 4 Rural $11,672,944 Cat. 12 Strategic Priority $25,609,195 TOTAL $37,282,139 Cat. 4R added $11.7M | Construction begins within 4 years | 2026-09-01 | Delayed from 6/22/24 to 9/1/2026
Laredo | Webb | 0037-10-040 | US 83 | 1 Miles North of SH 255 to Los Botines Ln | FY 2025-2028 | 50400000 | Widen Non-Freeway | Cat. 4 Rural $50,400,000 TOTAL $50,400,000 | Construction begins within 4 years | 2027-09-01
Laredo | Maverick | 0299-14-010 | SL 480 | US 57 to US 277 N | FY 2025-2028 | 119587049 | New Location Non-Freeway | Cat. 12 Strategic Priority $119,587,049 TOTAL 119,587,049 Cat. 12 increased $50.9M | Construction begins within 4 years | 2027-09-01 | Delayed from 5/3/27 to 9/1/2027
Laredo | Maverick | 0299-14-028 | SL 480 | 0.699 Miles South of US 277 to US 277 | FY 2028-2033 | 50891561 | Interchange at SL 480 | Cat. 4 Rural $50,891,561 TOTAL $50,891,561 | Construction begins in 5 to 10 years | 2027-05-03 | Project included in 2024 UTP but not the 2025 UTP
Sub-total US 277 | [5 empty] | 0
Sub-Total SL 480 | [5 empty] | 119587049
Sub-total US 83 | [5 empty] | 321152005
Sub-total IH 35 | [5 empty] | 638390651
2025 TOTAL Laredo District less TBD | [5 empty] | 1079129705 | 452668716
2024 TOTAL Laredo District less TBD | [5 empty] | 626460989 | 850660989
2023 TOTAL Laredo District less TBD | [5 empty] | 224200000

## Summary
FY 2025 UTP Project Totals
TxDOT District | FY 25 Amounts | FY 24 Amounts | Change | % Change | Construction Begun
Abilene | 19824000 | 16240000 | 3584000 | 22.07% | 0
Amarillo | 424998682 | 683775781 | -258777099 | -37.85% | 269063384
Laredo | 1079129705 | 626460989 | 452668716 | 72.26% | 0
Lubbock | 324603483 | 409365558 | -84762075 | -20.71% | 13080442
Odessa | 299538627 | 415452332 | -115913705 | -27.9% | 202949834
San Angelo | 18584232 | 3584000 | 15000232 | 418.5% | 0
Total 10-Year Amount | 2166678729 | 2154878660 | 11800069 | 0.5476% | 485093660